## Sheet1
MUNSN Schedule |  |  |  | Milestone 1 |  | Milestone 2 |  |  | Milestone 3 |  |  |  | Milestone 4
Task | 9 - 15 Jan | 16 - 22 Jan | 23 - 29 Jan | 30 Jan - 5 Feb | 6 - 12 Feb | 13 - 19 Feb | 20 - 26 Feb | 27 Feb - 5 Mar | 6 - 12 Mar | 13 - 19 Mar | 20 - 26 Mar | 27 Mar - 2 Apr | 3 - 9 Apr | 10 - 16 Apr | 17 - 23 Apr
1.0 Requirements Analysis
1.1 Requirements package due
1.2 Use Cases
1.3 Use Case Diagram
1.4 Functional Requirements
1.5 SRS Document
1.6 Traceability Matrix
1.7 Domain Model
1.7 Creation of schedule
2.0 Server Design
2.1 MongoDB Research
2.2 Look into hashing usernames for databases
2.3 Creating schemas for databases
2.4 Design e-mail server system
2.5 Entity diagram
2.6 Encryption protocol
2.7 Server REST API
3.0 Server Implementation
3.1.0 User Authentication/Email Confirmations
3.1.1 Friend Lists
3.1.2 Group Lists
3.2 HoganJS Templates implementation
3.3 Comment System Handler
3.4 Post System Handler
3.5 Polling system handler
4.0 Interface Design
4.1 Concept Design
4.2 Low Fidelity Wireframe Design
4.3 High Fidelity Wireframe Design
4.4 Lay Tags in HTML
4.5 Finalize all wireframes and prepare implementation
4.6 Interface functionality design
5.0 Interface Implementation
5.1 Front-back interfacing checks
5.2 Wireframe diagram-HTML conversion
5.3 Functionality Implementation
5.4 Testing
6.0 Front-Back Integration
TBD
7.0 Full System Testing
7.1 User log-in